## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | There is a functional link for sign in on the home page. 10/10/2019 JDR
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | The button correctly directs the user to the sign in page so the user can enter a username. 10/10/2019 JDR
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | The website correctly checks the username for an alphanumeric and reserves the name for the user. 10/10/2019 JDR
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | After testing, the system does reject the username if the requirements are not met. 10/10/2019 JDR
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | The system does not allow repeat names. 10/10/2019 JDR
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | The list of other signed in players do appear on the home page. 10/10/2019 JDR
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | Players are invisible to someone who is not signed in. 10/10/2019 JDR
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | Game correctly starts when you select a player. 10/10/2019 JDR
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | The game correctly displays the boards with the correct colors. 10/10/2019 JDR
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | Correctly displays and error. 10/10/2019 JDR
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | The user is correctly sent to the game board when another player challenges them to checkers. 10/10/2019 JDR
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | The game piece is not droppable yet. 10/10/2019 JDR
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | The piece is not moveable yet. 10/10/2019 JDR
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | It succesfully drops to an open location. 10/10/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | The pieces show up in the correct location for the player. 10/10/2019 JDR
Resignation | Given I am in a game of checkers, when I hit the sign out button then I will exit the web checkers game. |  |  | Pass | JDR, 11/4/2019
| Given I am in a game of checkers, when my opponent hits the sign out button then I will exit the web checkers game. |  |  | Pass | JDR, 11/4/2019
| Given I am in a game of checkers, when my opponent's idle timer runs out, then the game ends in a win for me. (see Story: Idle Timer) |  |  | Pass | JDR, 11/4/2019
| Given there is a game of checkers in progress, when both players are disconnected, then the game automatically ends. |  |  | Pass | JDR, 11/4/2019
Simple Move | Given I am in a game of checkers when my turn starts then I expect movable pieces to be marked in some way. |  |  | Pass | JDR, 11/5/2019
| Given I am in a game of checkers and it is my turn and there are no pieces I can jump when I click on a movable piece and then a square to move it on then the piece should move there if it is a legal move. |  |  | Pass | JDR, 11/5/2019
Single Jump | Given a valid single jump move exists when I make said move then I expect to capture the enemy piece. |  |  | Pass | JDR, 11/5/2019
| Given one of my pieces can make a jump when my turn starts then I expect to be required to make that move. |  |  | Pass | JDR, 11/5/2019
Multiple Jump Move | Given one of my pieces is in a position where multiple jumps in one turn are possible when my turn starts then I expect to be required to make that move. |  |  | Pass | JDR, 11/5/2019
| Given one of my pieces is in a position to make multiple jumps in one turn when my turn starts then I expect that point to be highlighted as the only valid move, along with any other valid multi-jump moves there might be. |  |  | Pass | JDR, 11/5/2019
| Given one of my pieces is in a position to make more than one multi-jump when I start my turn then I expect to be able to choose any route that results in multiple pieces taken, even if the route I take does not result in as many taken pieces as another. |  |  | Pass | JDR, 11/5/2019
Player Services | Given model data needs to be modified when in a ui-tier object when we modify it then the code runs through PlayerServices. |  |  | Pass | JDR, 11/5/2019
| Given a user starts a session when the player enters the home route for the first time then there should be a new session attribute containing a new instance of PlayerServices. |  |  | Pass | JDR, 11/5/2019
Upgrade | Given a player makes it to the opposite end of the board when I move to one of the spaces at the row at the other end of the board then I expect to become a king. |  |  | Pass | JDR, 11/5/2019
| Given I am a king when I go to make a move then I expect be able to move in two different directions. |  |  | Pass | JDR, 11/5/2019
Sign Out
As a user I want to make multi-jumps on one turn so that the game can go more smoothly. | Given that I have a valid multi jump available when it is my turn then I expect to be able to do a multi-jump clickling 'submit turn' only once.
As a user I want the server to ask me if I want to save a replay of a just-finished game so that I will be able to find them later. | Given that I have finished a checkers game when the game finished then I want to be able to click 'save game' to save my game.
As a user I want to be able to play back games so that I can review what happened | Given that I am a logged in user when I am on the home screen then I want the option to be able to replay games
Spectating | Given that I am a logged in user when I am selecting a game mode then I want to be able to choose 'spectator' to view other's games.
Code Coverage | Given that I am a dev, when I am doing unit tests then I want code coverage of at least 80%